## Slide 1
TROUBLESHOOTING
& RESPONSIBLE PROJECT PIVOTS
STARLAB Deck 08 • Unit 3 Core Instruction
Notes: PRIMARY TEACHING MOMENT
Unit 3, Week 6
REQUIRED WEEK 6 MATERIALS
- Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log
- Unit 3 Student Handout 5: Method Revision Decision Chart
- Unit 3 Appendix D: Types of Research Problems
- Unit 3 Appendix E: Troubleshooting Sentence Frames
REVISIT / SECONDARY USE
Week 7 required: Student Handouts 6-7; Appendices F-G
Week 10 required: Student Handouts 11-12
Week 10 optional / teacher reference: Appendices K-L
Week 13 required: Student Handouts 9 and 15
Week 13 optional / teacher reference: Appendix P
RESOURCE ALIGNMENT
Use this deck whenever a project stalls, pivots, or needs structured revision. Print each later resource in its assigned week rather than as part of the Week 6 packet.

## Slide 2
WHEN RESEARCH GETS MESSY
The purpose of troubleshooting is to make the project stronger.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 02
A problem is not the end of the project.
A problem is evidence that the method, design, measurement, or timeline needs attention.
• Real research rarely follows the first plan exactly.
• Pilot testing is designed to reveal weaknesses early.
• The goal is not to hide problems; the goal is to respond responsibly.
Today’s move: diagnose → revise → document → continue.
Notes: Teacher notes:
Open by reassuring students that problems are expected. Ask for examples of what has already gone wrong during pilot testing. Keep the tone practical and calm: problems are not personal failures. The goal is to turn vague frustration into a specific research problem that can be acted on.
Resource alignment:
Use after students have completed Unit 3 Student Handout 1: Pilot Test Plan and begun documenting work with Unit 3 Student Handout 3: Daily Research Journal Entry Template. This slide sets up later use of Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log.

## Slide 3
FAILURE IS DATA
A failed trial can teach you what the next trial needs.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 03
NOT USEFUL
“I messed up. The project is bad.”
USEFUL
“The sensor drifted after 3 minutes, so I need to recalibrate between trials.”
The shift is from emotion to evidence.
• What happened?
• How do you know?
• What might have caused it?
• What will you try next?
Notes: Teacher notes:
Students may see failure as embarrassing. Emphasize that a failed trial is only wasted if it is undocumented or ignored. Invite one student to translate an emotional reaction into an evidence-based observation. Reinforce the shift from 'I messed up' to 'Here is what happened, here is the evidence, and here is what I will test next.'
Resource alignment:
Use with Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log. Also connect to Unit 3 Appendix E: Troubleshooting Sentence Frames for students who need language to describe problems productively.

## Slide 4
SIX COMMON RESEARCH PROBLEMS
Most issues fall into a recognizable category.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 04
PROCEDURE
The steps are unclear, incomplete, or inconsistent.
MEASUREMENT
The tool or method does not capture useful data.
EQUIPMENT / MATERIALS
A part, material, or tool fails or behaves unpredictably.
DESIGN / PROTOTYPE
The build or setup cannot be tested as planned.
DATA RECORDING
Data exist, but they are not organized or usable.
TIMELINE / SCOPE
The project is too large for the remaining time.
Notes: Teacher notes:
Use this slide as the organizing framework for the deck. Have students quickly classify a current project issue into one of these categories. Most problems involve more than one category, which is fine. The point is to help students name the problem before they start changing the project.
Resource alignment:
Use with Unit 3 Appendix D: Types of Research Problems. Students can also record the category in Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log.

## Slide 5
DIAGNOSE BEFORE YOU FIX
Do not change everything at once.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 05
1
OBSERVE
What exactly happened?
2
EVIDENCE
What proof shows this is the issue?
3
CAUSE
What might explain it?
4
ACTION
What single change will you test?
Bad troubleshooting changes several variables at once. Good troubleshooting changes one thing, records it, and checks whether it worked.
Notes: Teacher notes:
This is a key research habit: students often make five changes at once and then cannot tell what actually helped. Reinforce the phrase 'one change, one reason, one record.' Push students to observe first, identify evidence, propose a cause, and then test one action.
Resource alignment:
Use with Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log and Unit 3 Student Handout 11: Troubleshooting Conference Prep. This slide also supports Unit 3 Appendix E: Troubleshooting Sentence Frames.

## Slide 6
PROCEDURAL PROBLEMS
The steps do not produce consistent, repeatable work.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 06
• A step is missing or vague.
• Timing differs between trials.
• Conditions are not kept the same.
• The order of steps changes.
• Cleanup or reset steps are unclear.
Ask:
• Could another student follow this without guessing?
• What is changing between trials?
• What needs to be written more precisely?
Fix: revise the procedure and document what changed.
Notes: Teacher notes:
Connect this to the Revised Procedure Template. Procedural problems are common and easy to improve when students write the steps more precisely. Ask students whether another student could repeat their procedure without guessing. If the answer is no, the procedure needs revision before more data are collected.
Resource alignment:
Use with Unit 3 Student Handout 6: Revised Procedure Template and Unit 3 Appendix F: Procedure Revision Checklist. If students are deciding whether they are ready for full data collection, also use Unit 3 Student Handout 5: Method Revision Decision Chart.

## Slide 7
MEASUREMENT PROBLEMS
The data do not answer the question clearly.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 07
A measurement problem means the project may be working, but the evidence is weak.
01
Tool is not precise enough
02
Units are missing or inconsistent
03
Readings drift over time
04
Measurement timing varies
05
Data table does not capture key information
Fix: improve the measurement method before collecting more weak data.
Notes: Teacher notes:
Ask students to show their data table. If the data table cannot record the evidence needed, the measurement plan is not ready. Emphasize that measurement problems can make a promising project produce weak evidence, so they should be addressed before students collect more data.
Resource alignment:
Use with Unit 3 Student Handout 7: Data Table Audit. If students are actively collecting data, connect to Unit 3 Student Handout 8: Formal Data Collection Log. If they need to revisit planning, connect to Unit 2 Student Handout 8: Data Collection Plan.

## Slide 8
EQUIPMENT AND MATERIAL PROBLEMS
Sometimes the tool, part, or material is the weak link.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 08
Examples
• Loose wire or unstable sensor
• Prototype part breaks before testing
• Material absorbs water unexpectedly
• Battery voltage drops during trials
• Software or code produces inconsistent output
Document like a researcher:
• What failed?
• When did it fail?
• How did it affect the data?
• What repair or replacement was made?
• Does the trial need to be flagged?
Notes: Teacher notes:
Emphasize that equipment issues must be documented, especially if they affect a trial. A broken part is not just a problem; it can explain variation or invalid data later. Ask students to identify whether a trial should be flagged, repeated, or kept with a note.
Resource alignment:
Use with Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log and Unit 3 Student Handout 3: Daily Research Journal Entry Template. This also connects to Unit 3 Appendix D: Types of Research Problems.

## Slide 9
DESIGN OR PROTOTYPE PROBLEMS
The design itself may need revision.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 09
A design problem is deeper than a bad trial.
• Prototype cannot survive basic testing.
• Setup does not isolate the intended variable.
• Design does not meet safety expectations.
• Performance metric is not meaningful.
• Failure mode reveals a structural weakness.
Research response:
• Analyze the failure.
• Revise one design feature.
• Retest under the same conditions.
• Compare evidence across versions.
Engineering projects often learn the most from controlled failure.
Notes: Teacher notes:
Engineering students often experience prototype failure. Make sure they do not interpret this as 'no data.' Failure mode, load at failure, time to failure, and redesign reasoning are all data. Encourage students to compare versions under consistent conditions.
Resource alignment:
Use with Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log, Unit 3 Student Handout 5: Method Revision Decision Chart, and Unit 3 Appendix K: Responsible Project Pivots.

## Slide 10
TIMELINE AND SCOPE PROBLEMS
Sometimes the project is too large for the time remaining.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 10
Warning signs
• Materials still not available
• Full data collection would take too long
• Too many variables
• Too many prototype versions
• No usable data by the midpoint
Responsible response
• Reduce scope
• Test fewer conditions
• Frame as a pilot study
• Focus on one meaningful comparison
• Create a documented recovery plan
Smaller and defensible beats ambitious and incomplete.
Notes: Teacher notes:
This slide should reduce shame around scope reduction. Make clear that a project can still be strong if it becomes a pilot study, feasibility study, focused comparison, or failure analysis. Smaller and defensible is better than ambitious and incomplete.
Resource alignment:
Use with Unit 3 Student Handout 9: Weekly Progress Check-In and Unit 3 Appendix P: Recovery Plan Options. Later in Unit 3, this can also connect to Unit 3 Student Handout 15: Post-Progress Report Action Plan.

## Slide 11
THE TROUBLESHOOTING LOG
Your fix is only scientific if it is documented.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 11
Problem observed
Evidence
Possible cause
Proposed fix
Approval needed?
Result of fix
Handout match: Student Handout 4 — Pilot Test Reflection and Troubleshooting Log
Notes: Teacher notes:
Pause here and have students open the troubleshooting log. If time allows, have them complete the first two sections for a real problem from their project. Students should write what happened and what evidence shows the problem before proposing a fix.
Resource alignment:
Primary resource: Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log. Use Unit 3 Appendix E: Troubleshooting Sentence Frames for students who need support writing precise troubleshooting language.

## Slide 12
RESPONSIBLE PROJECT PIVOTS
A pivot is not quitting. It is a justified change in direction.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 12
A responsible pivot...
• Preserves the core purpose when possible.
• Is based on evidence or feedback.
• Is approved before testing continues.
• Includes a revised question, method, or data plan.
• Is documented in the research journal.
A weak pivot...
• Happens because the project got hard.
• Avoids documentation.
• Ignores safety or approval.
• Changes the goal without a new evidence plan.
• Abandons useful failure data.
Notes: Teacher notes:
Students need a way to distinguish productive pivots from avoidance. Invite examples: a safer method, fewer variables, a smaller comparison, a shift to a pilot study, or a move from full build to feasibility testing. A responsible pivot is evidence-based and approved, not impulsive.
Resource alignment:
Use with Unit 3 Appendix K: Responsible Project Pivots. If the pivot requires outside guidance, connect to Unit 3 Student Handout 12: Mentor or Expert Feedback Log and Unit 3 Appendix L: Mentor Communication Guidelines.

## Slide 13
PIVOT DECISION FLOW
Use evidence to choose the next move.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 13
Problem identified
Can one revision fix it?
Revise + retest
Reduce scope or pivot
Document + seek approval
YES
NO
Key rule: no major pivot happens silently.
Notes: Teacher notes:
Use this as a quick decision protocol. It also reinforces approval before major changes. Ask students which box they are currently in: revise and retest, reduce scope, pivot, document, or seek approval. Do not allow major project changes to happen silently.
Resource alignment:
Use with Unit 3 Student Handout 5: Method Revision Decision Chart and Unit 3 Appendix K: Responsible Project Pivots. Students should document the decision in Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log or in their research journal.

## Slide 14
ACTIVITY: DIAGNOSE THE SCENARIO
Classify the problem before proposing a fix.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 14
STUDENT ACTIVITY
1.
A sensor reads 0 for every trial, even when conditions change.
2.
A student changed the ramp height halfway through testing but kept the same data table.
3.
A prototype breaks before the planned load test can begin.
4.
The project requires 6 more weeks of growth data, but only 2 weeks remain.
Task: Identify the problem type, the evidence, and one responsible next step.
Notes: Teacher notes:
Student-facing activity. Students can work individually first, then compare with a partner. Aim for the reasoning, not one perfect category. Scenarios map to measurement, procedure/data recording, design/prototype, and timeline/scope. Ask students to name evidence before proposing a fix.
Resource alignment:
Use with Unit 3 Appendix D: Types of Research Problems and Unit 3 Appendix E: Troubleshooting Sentence Frames. Students may record scenario responses on Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log as practice before applying it to their own project.

## Slide 15
ACTIVITY: TROUBLESHOOTING CONFERENCE
Use a structured conversation instead of vague help-seeking.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 15
STUDENT ACTIVITY
1
Researcher explains the problem in 2 minutes.
2
Group asks clarifying questions only.
3
Group suggests possible causes.
4
Group suggests possible next steps.
5
Researcher chooses one action and documents it.
Handout match: Troubleshooting Conference Prep
Notes: Teacher notes:
This activity is especially useful during project work days. Groups of 3–4 can rotate through one problem per student. Enforce the clarifying-questions-only step to slow down premature advice. The goal is a documented next action, not a loose conversation.
Resource alignment:
Use with Unit 3 Student Handout 11: Troubleshooting Conference Prep. If students receive outside feedback, use Unit 3 Student Handout 12: Mentor or Expert Feedback Log.

## Slide 16
ACTIVITY: REVISE, RETEST, OR PIVOT?
Choose the smallest responsible next move.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 16
STUDENT ACTIVITY
For your own project, answer:
• What is the main problem right now?
• What evidence shows it is a problem?
• Can one revision fix it?
• Do you need approval before continuing?
• Will you revise, retest, or pivot?
Exit product:
Complete one Troubleshooting Log entry and update your next research journal entry.
One change. One reason. One record.
Notes: Teacher notes:
This is the main work-time activity. Students should produce a documented decision, not just talk about what they might do. Push for the smallest responsible next move: revise, retest, seek approval, reduce scope, or pivot.
Resource alignment:
Use with Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log and Unit 3 Student Handout 5: Method Revision Decision Chart. Students should also update Unit 3 Student Handout 3: Daily Research Journal Entry Template or their active research journal. Use Unit 3 Appendix K: Responsible Project Pivots if the next move changes the project direction.

## Slide 17
EXIT TICKET
Leave with a responsible next step.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 17
EXIT TICKET
Write three sentences:
The problem I need to troubleshoot is _____.
The evidence that shows this problem is _____.
My next approved step is _____ because _____.
Submit or attach this to today’s research journal entry.
Notes: Teacher notes:
Use this to ensure every student leaves with a specific next action. It also creates documentation for progress monitoring. Students who cannot identify evidence for the problem need a short conference before they keep working.
Resource alignment:
Use as a quick checkpoint after Unit 3 Student Handout 4: Pilot Test Reflection and Troubleshooting Log or Unit 3 Student Handout 11: Troubleshooting Conference Prep. Students should attach the exit ticket to today’s research journal entry or use it to complete Unit 3 Student Handout 9: Weekly Progress Check-In.

## Slide 18
NEXT DECK
DATA ORGANIZATION:
RAW DATA VS. CLEAN DATA
You cannot analyze evidence you cannot understand.
Next, students organize raw records into clean, usable data.
STARLAB Deck 08 • Troubleshooting & Responsible Project Pivots • 18
Notes: Teacher notes:
Close by connecting troubleshooting to data quality. If changes are undocumented, later data analysis becomes unreliable. Preview the next deck as the transition from project work to organized evidence. Students should understand that clean analysis depends on honest documentation of problems and revisions.
Resource alignment:
Next deck connection: Deck 9: Data Organization — Raw Data vs. Clean Data. This transition connects to Unit 3 Student Handout 17: Data Audit and Organization Checklist and Unit 3 Student Handout 18: Unit 3 Readiness for Analysis Review. It also previews Unit 4 Student Handout 1: Raw Data Inventory and Unit 4 Student Handout 2: Clean Data Set Builder.