### Why We Are Doing This

For the first time, you are running a long-term research or engineering project that takes months to complete. That means you need to learn how to plan like a real researcher: setting goals, staying organized, and adjusting when things do not go as expected. Your Weekly Progress Tracker is your project’s roadmap and your accountability record.

## 1. Understanding the Tracker’s Purpose

Your STARLAB tracker is not just busywork. It is a professional research log designed to help you:

- Break your large project into manageable weekly goals.

- Track what has been completed and what is next.

- Reflect on what is working or not working.

- Stay aligned with your mentor and teacher during weekly meetings.

- Build a visible record of effort and iteration that supports your final poster grade.

## 2. Setting Up Your Plan

Start by opening your tracker and looking at all 12 rows (weeks). Then follow these steps:

### Step 1: Start from Your End Goal

Think about your final deliverable (poster and presentation). Ask yourself:

- What needs to be finished by the end?

- What data or prototype must I have by then?

- What smaller steps get me there?

Example:
Goal: Build and test an Arduino-controlled soil moisture sensor.
End Deliverable: Working prototype, calibration data, and final poster.

Major tasks might be:

- Research sensor circuit and code examples.

- Order and test components.

- Build prototype.

- Collect calibration data.

- Analyze accuracy and reliability.

- Prepare visuals and poster.

### Step 2: Assign Tasks to Weeks

Open your tracker and give each week a clear, realistic goal in the Main Goals / Objectives column. Each week’s goal should be something you can finish by the end of that week.

| Week | Main Goal | Notes |
| --- | --- | --- |
| 1 | Finish research and finalize method | Review two or three published studies |
| 2 | Collect first round of data | Record at least five trials |
| 3 | Re-run data collection with changes | Adjust sample size |
| 4 | Begin analyzing results | Use spreadsheet formulas |
| 5 | Graph and interpret results | Look for patterns or errors |
| 6 | Draft poster figures | Screenshots and data visuals |

Tip: Do not try to plan every week perfectly at the start. Fill in your first four or five weeks, then refine as you go.

### Step 3: Use the Status Column Wisely

Every Friday:

- Mark each row as Not Started, In Progress, or Complete.

- If you had trouble that week, do not check Complete. Write what went wrong under Challenges / Issues.

- Rows will color themselves automatically to help you see progress at a glance.

## 3. Thinking Ahead: Long-Term Planning Tips

A. Always Plan One Week Ahead
At the end of each class period or week, fill in the Next Steps column. This becomes your starting goal for the following week.

B. Expect Things to Go Wrong
Science and engineering rarely go smoothly. Schedule extra time for troubleshooting, redesigns, or repeating tests.

C. Use Mentors Strategically
If you are stuck, write a specific question or problem in the Challenges column before your meeting. That is what your mentor feedback time is for.

D. Show Evidence
Whenever you mark something as Complete, make sure you have evidence: data file, photo, graph, or screenshot that can later go into your poster.

E. Review the Dashboard
Use the Dashboard sheet to see your overall progress. The bar chart and percentage show whether you are staying on schedule.

## 4. Example Planning Scenario

Project: Testing recycled plastics as concrete reinforcement

| Week | Main Goals / Objectives | Tasks Completed | Challenges / Issues | Next Steps | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Review literature and select materials | Found three sources, selected nylon and PET | Needed mix ratio information | Contact mentor about ratios | In Progress |
| 2 | Prepare first concrete batch | Mixed nylon sample | Inconsistent curing time | Adjust water ratio and prepare mold | In Progress |
| 3 | Test compressive strength | Tested three samples | One broke early | Dry longer before next test | Complete |
| 4 | Analyze data and graph results | Graph complete | Low sample size | Make three more samples | In Progress |

## 5. How You Will Be Supported

- Weekly STARLAB Meetings: You will review your tracker with your mentor or teacher. Be ready to explain what you did and what is next.

- Midpoint Review: Around week six, we will look for trends and address any red flags such as too many weeks marked In Progress.

- End-of-Semester Reflection: You will write a short summary about what you learned about project management and iteration.

## 6. Your Responsibility

By keeping your tracker accurate and honest, you are learning the skill that separates amateurs from professionals: the ability to manage your own research process.

Treat the tracker as your project’s heartbeat. If it is up to date, your project is healthy.