Program: STARLAB (Student Research & Technology Lab)
Year / Semester: ________________________
Name/Project: _____________________________Purpose

The STARLAB Research Tracker is designed to help you manage your independent research or engineering project with the professionalism of a university or professional research team. It will serve as your ongoing project journal, documenting your weekly goals, accomplishments, challenges, and reflections.  Consistent use of this tracker demonstrates your accountability, planning skills, and scientific or engineering process maturity, all key outcomes of the STARLAB program.

How the Tracker Works

### Weekly Progress Log

Each week, you will complete one row in your tracker spreadsheet. The sheet includes the following columns:

| Column | Description |
| --- | --- |
| Week # | Sequential week of the semester or project. |
| Date Range | The Monday–Friday (or relevant) week dates. |
| Main Goals / Objectives | What you plan to achieve this week. |
| Tasks Completed | Specific steps, experiments, or design changes you actually finished. |
| Challenges / Issues | Problems you encountered (equipment, time, data, communication, etc.). |
| Next Steps | What you’ll do next week to move forward or resolve issues. |
| Mentor or Teacher Feedback | Notes from your weekly check-in with your mentor or teacher. |
| Status | Dropdown menu: Not Started, In Progress, or Complete. This will color-code your row automatically. |

Expectations

- Update Weekly:
 Fill out your progress row each week (by end of class on Friday or by Sunday night if working outside class). Missing weeks = project falling behind = lower process score.

- Be Detailed and Accurate:
 Your weekly notes should read like a short lab log or engineering design journal: clear, specific, and meaningful. Don’t use “did stuff” or “worked on project” without telling what you did and why.

- Status Accuracy:
 Use the dropdown realistically. Mark “Complete” only once you’ve actually finished the tasks and have documented evidence (data, prototype photo, graph, etc.).

- Professionalism:
 Write in clear, professional language suitable for scientific or engineering work. Avoid slang, vague phrases, and incomplete ideas.

Weekly Check-Ins

- Day: Time will be found during STARLAB class (or by appointment)

- Duration: 5–10 minutes per student/project team

- Purpose: Discuss your tracker, review your progress, address roadblocks, and plan next steps.

- Mentor Feedback: Notes from the meeting will be entered into your “Mentor or Teacher Feedback” column.

If you miss your check-in, you must schedule a make-up meeting during regular STARLAB time or office hours.

Evaluation Criteria

You will be evaluated on both completion and quality of your tracker entries:

| Category | Description | Weight |
| --- | --- | --- |
| Consistency | Updated weekly without missing weeks | 30% |
| Depth of Reflection | Entries include thoughtful analysis of challenges, next steps, and reasoning | 30% |
| Progress Tracking Accuracy | Status and milestones reflect true project progress (not just optimistic) | 20% |
| Professionalism & Clarity | Clear writing, no slang, entries are well-structured | 10% |
| Mentor Responsiveness | You respond to and implement mentor/teacher feedback in your logs | 10% |

Note: The tracker is part of your Research Journal/Documentation grade in the STARLAB Rubric, and will contribute to 20% of your overall grade.

Dashboard Overview

The spreadsheet includes a built-in Dashboard sheet, which automatically calculates:

- Number of weeks completed

- Percentage of weeks marked “Complete”

- Bar chart of week counts by status (Not Started / In Progress / Complete)

- Keyword flags (looking for recurring issues like equipment, data, time, materials, permission, safety)

You do not need to edit the Dashboard sheet. It’s for the teacher/mentor to monitor overall progress and identify projects that need additional support.

Staying On Track

- Set weekly goals at the start of each week — don’t just think long-term, focus on what you’ll this week finish.

- Log small wins — everything counts (data cleaning, prototype tweak, literature review).

- Flag challenges early — better to note a delay than hide it; your mentor can help if you’re honest.

- Update Next Steps at the start of each new week — what’s your plan?

- File naming & organization: Use a consistent naming scheme like Lastname_ProjectTitle_ProgressTracker.xlsx (or Google Sheets link) so it’s easy to find.

- Backup your work: keep a copy in Google Drive or in your STARLAB folder so nothing gets lost.

End-of-Semester Expectation

By the end of your project, your tracker should:

- Contain a completed weekly row for each week of your project term.

- Show iteration, reflection, and progress over time (not just “finished quickly”).

- Be review-ready.  Your teacher and mentor can open it, see your logs, check your growth, and link it to your Mid-Project Progress Report presentation.

Signature & Mentor Verification

I understand the expectations of the STARLAB Weekly Progress Tracker and commit to updating it weekly with honesty and accuracy.

Student Name: ___________________________
Student Signature: ______________________
Date: _________________________________

Mentor/Teacher Name: ____________________
Signature: ______________________________
Date: _________________________________