STARLAB

Showcase Planning Kit

Teacher-facing resources for planning, running, and reflecting on a STARLAB research showcase

Purpose: This kit helps teachers convert student research products into a polished public event that celebrates authentic research while keeping student explanations evidence-based, professional, and accessible to guests.

# How to Use This Kit

This document is designed for teachers who are preparing a STARLAB final presentation event, public showcase, research night, poster session, or mentor panel. It can be used as a standalone planning packet or divided into separate portal resources.

Use Sections 1-3 to choose the showcase format, timeline, and logistics.

Use Sections 4-7 to prepare students, visitors, mentors, and evaluators.

Use Sections 8-11 during the event and immediately afterward.

Adapt names, dates, locations, rubrics, and communication language to match local school expectations.

## Recommended Portal Placement

Teacher Portal > Showcase Planning

Unit 6 folder > Showcase preparation resources

Mentor and Community Partner Toolkit > Showcase invitation and visitor roles

Parent/Guardian Communication Pack > Showcase invitation and celebration messages

# Quick Start Checklist

| Timeline | Teacher Action | Student Action |
| --- | --- | --- |
| 6-8 weeks before | Choose event format, date, audience, space, and basic schedule. | Confirm project status and likely presentation product. |
| 4-5 weeks before | Invite visitors, mentors, administrators, families, and community partners. | Begin refining visual product and research story. |
| 3 weeks before | Confirm technology, tables, room layout, feedback forms, and assessment method. | Practice 30-second, 2-minute, and formal explanations. |
| 2 weeks before | Create station map, speaking order, visitor instructions, and backup plan. | Complete Q&A preparation and visual product final check. |
| 1 week before | Print signage, rubrics, feedback forms, name cards, and schedule. | Complete final rehearsal and professionalism expectations. |
| Event day | Facilitate setup, welcome visitors, manage flow, assess presentations, and collect feedback. | Present professionally, answer questions, and document audience feedback. |
| After event | Thank guests, collect reflections, archive artifacts, and note improvements for next year. | Complete post-presentation reflection and portfolio updates. |

# 1. Choosing the Showcase Format

The best format depends on class size, available space, audience size, technology access, and whether the goal is celebration, assessment, public outreach, or mentor feedback. A school may also combine formats.

| Format | Best For | Teacher Notes |
| --- | --- | --- |
| Poster Session | Many students, public guests, families, administrators, and informal conversation. | Students stand by posters or boards and repeat short explanations. This is usually the easiest public showcase format. |
| Formal Presentation Session | Smaller groups, class assessment, mentor panel, or auditorium-style event. | Students present once to an audience. Easier to assess deeply, but less flexible for large groups. |
| Rotating Gallery Walk | Classroom practice, peer review, or limited space. | Half the class presents while the other half rotates, then groups switch. |
| Mentor Panel | Students with external mentors, technical projects, or continuation potential. | Mentors ask questions and provide feedback. Good for advanced students, but requires scheduling. |
| District Research Night | Public celebration, program advocacy, superintendent or board visibility. | Requires more logistics, but can build long-term support for STARLAB. |
| Hybrid Showcase | Schools wanting both formal presentation and public poster interaction. | Students may give a brief formal talk, then move to poster stations. |

## Recommended Starting Point for New STARLAB Chapters

For a first-year implementation, use a poster-session style event with repeated 2-minute explanations. This format gives students more practice talking about their work, reduces the pressure of a single speech, and allows visitors to ask authentic questions.

# 2. Showcase Timeline

| When | Planning Tasks |
| --- | --- |
| 8 weeks before | Choose date, location, format, and audience. Confirm whether event will be during class, evening, advisory period, or school-day showcase. |
| 6 weeks before | Reserve room or space. Identify technology, table, power, and display needs. Notify administration. |
| 5 weeks before | Send save-the-date invitations to mentors, administrators, families, and community partners. |
| 4 weeks before | Students complete visual aid planning and begin presentation practice. Create visitor feedback forms and rubrics. |
| 3 weeks before | Finalize event format, station map, presentation order, guest roles, and assessment method. |
| 2 weeks before | Students complete formal practice presentations and mock Q&A. Teacher confirms technology and printing. |
| 1 week before | Print signs, station labels, schedules, rubrics, and visitor question guides. Run final rehearsal. |
| Event day | Set up early. Welcome guests. Monitor flow. Collect feedback. Celebrate student work. |
| 1-3 days after | Students complete reflection. Teacher sends thank-you messages and archives artifacts. |

# 3. Event Logistics Checklist

| Category | Checklist Items |
| --- | --- |
| Space | Reserve room, hallway, library, commons, auditorium, or lab space. Confirm capacity and traffic flow. |
| Furniture | Tables, chairs, display boards, easels, poster stands, sign-in table, judging table, water table if allowed. |
| Technology | Projector, screens, laptops, chargers, extension cords, power strips, adapters, speakers, backup devices. |
| Displays | Posters, boards, slides, prototypes, models, printed graphs, QR codes, research journals, reports. |
| Safety | No hazardous demonstrations during public events without explicit approval. Use signs for fragile or do-not-touch materials. |
| Guest Flow | Welcome table, station map, visitor instructions, feedback forms, name tags, rotation schedule. |
| Assessment | Rubrics, teacher clipboard, feedback forms, station list, presentation order, scoring system if used. |
| Documentation | Photo/video permission check, camera, student artifact collection, post-event archive folder. |
| Backup Plans | Absent student plan, technology failure plan, poster printing failure plan, overflow audience plan. |
| Cleanup | Assigned cleanup roles, trash/recycling, borrowed equipment return, room reset expectations. |

## Room Layout Options

| Layout | Description | Best Use |
| --- | --- | --- |
| Perimeter Stations | Student stations around the room perimeter with visitors circulating freely. | Poster session or open house. |
| Rows of Tables | Tables arranged in aisles with wide walking lanes. | Large showcase or library/commons event. |
| Presentation Zone + Poster Zone | One area for short talks and another for poster conversations. | Hybrid event. |
| Mentor Panel Setup | Students present at front; mentors or evaluators sit together. | Formal defense or technical feedback. |

# 4. Student Preparation Plan

Students should not enter the showcase with only a finished poster. They need repeated oral practice, evidence-based Q&A preparation, and a clear understanding of how to explain limitations.

| Preparation Area | Student Task | Related STARLAB Resources |
| --- | --- | --- |
| Research Story | Prepare one-sentence research story, project purpose, method, strongest evidence, conclusion, limitation, and future work. | Unit 6 Student Handout 2: Research Story Refinement |
| Three Explanation Lengths | Practice 30-second, 2-minute, and formal presentation versions. | Unit 6 Student Handout 3: Three-Length Presentation Practice |
| Visual Product Check | Verify title, question, methods, evidence, conclusion, limitations, captions, and readability. | Unit 6 Student Handout 11: Presentation Product Final Check |
| Q&A | Prepare evidence-based answers to likely questions. | Unit 6 Student Handouts 7-9 |
| Professionalism | Review expectations for greeting guests, answering questions, staying at station, and cleanup. | Unit 6 Student Handout 12: Professionalism and Showcase Expectations |
| Reflection | Collect feedback and complete reflection after the event. | Unit 6 Student Handouts 13-15 |

# 5. Student Showcase Readiness Checklist

| Student Readiness Item | Complete? | Notes |
| --- | --- | --- |
| Final visual product is complete or presentation-ready. |  |  |
| Research question or engineering goal is visible. |  |  |
| Key data are shown clearly with labels and units. |  |  |
| Conclusion is evidence-based and appropriately cautious. |  |  |
| Limitations and future work are included. |  |  |
| Student can give a 30-second explanation. |  |  |
| Student can give a 2-minute explanation. |  |  |
| Student can give a formal explanation if required. |  |  |
| Student has practiced answering questions. |  |  |
| Student can explain the strongest evidence and one limitation. |  |  |
| Prototype or demonstration, if used, is safe and approved. |  |  |
| Backup copy of slides or digital files is available. |  |  |

# 6. Visitor Invitation Templates

## Save-the-Date Message

Subject: Save the Date: STARLAB Student Research Showcase

Dear [Name],

You are invited to attend our STARLAB Student Research Showcase on [date] at [time] in [location]. Students in STARLAB have spent the year developing, testing, analyzing, and communicating original scientific or engineering research projects. The showcase will give students an opportunity to explain their work, share evidence, discuss limitations, and answer questions from an authentic audience.

We would be honored to have you attend, ask students thoughtful questions, and help celebrate the work they have done as developing researchers.

Sincerely,

[Teacher Name]

## Formal Invitation Message

Subject: Invitation to Attend the STARLAB Student Research Showcase

Dear [Name],

Our STARLAB students are preparing to present their yearlong research projects, and we would like to invite you to join us for the final showcase. Students will present scientific and engineering work through posters, visual aids, prototypes, data displays, and conversations with guests.

The event will take place on [date] from [start time] to [end time] at [location]. Visitors are encouraged to ask students questions about their research question, method, data, limitations, and next steps. No specialized science background is required; thoughtful curiosity is exactly what students need from an authentic audience.

Thank you for supporting student research and helping build a culture of scientific inquiry in our school community.

# 7. Visitor Guide

## Purpose for Visitors

You are not expected to judge students harshly or know everything about their topics. Your role is to listen carefully, ask thoughtful questions, and help students practice communicating research to a real audience.

## Suggested Visitor Questions

What question were you trying to answer or what problem were you trying to solve?

Why did you choose this project?

How did you collect your data or test your design?

What was your most important result?

What does this graph or visual show?

What surprised you during the project?

What was the hardest problem to solve?

What limitation affected your project?

What would you do next if you continued this work?

What did you learn about research from this experience?

## Visitor Feedback Form

| Prompt | Response |
| --- | --- |
| Student/project visited: |  |
| One strength of the presentation was: |  |
| The most helpful evidence or visual was: |  |
| One thoughtful question I still have is: |  |
| One suggestion for continued work is: |  |
| Something I learned from this student was: |  |

# 8. Mentor or Evaluator Role Guide

Mentors and evaluators may provide deeper feedback than general visitors, but the tone should remain supportive. The goal is to help students think like scientists and engineers, not to catch them in mistakes.

| Evaluation Focus | What to Look For |
| --- | --- |
| Research Understanding | Can the student explain the purpose, question, method, evidence, and limitations? |
| Evidence Explanation | Does the student use specific data, visuals, observations, or prototype results to support claims? |
| Method Awareness | Can the student explain why the method was chosen and what changed during the project? |
| Limitations | Does the student acknowledge uncertainty, error, limited trials, scope, or design constraints? |
| Future Work | Can the student identify a realistic next step based on evidence? |
| Professionalism | Does the student communicate clearly, listen carefully, and respond respectfully? |

# 9. Showcase Day Run-of-Show

| Time | Action |
| --- | --- |
| Before event | Students set up stations. Teacher checks safety, technology, signage, station map, and visitor materials. |
| Opening | Teacher or administrator welcomes guests, explains STARLAB, and gives visitor instructions. |
| Round 1 | Visitors circulate. Students give short explanations and answer questions. |
| Transition | Optional pause for announcements, station switch, or informal viewing. |
| Round 2 | Visitors continue circulating or students rotate if using a split format. |
| Closing | Thank students, visitors, mentors, families, and partners. Invite final conversations. |
| After event | Students clean stations, save feedback, and complete reflection as soon as possible. |

## Sample Welcome Script

Good evening, and thank you for joining us for the STARLAB Student Research Showcase. STARLAB stands for Science Through Advanced Research, Learning, Application, and Building. This course asks students to move beyond traditional labs and experience the full arc of research: asking a question, designing a plan, collecting evidence, analyzing data, communicating results, and reflecting on limitations.

Tonight, you will hear students explain not only what they found, but how they worked through uncertainty. Please ask questions, encourage them to point to evidence, and invite them to explain what they would do next. Thank you for helping create an authentic audience for student research.

# 10. Showcase Rubric

| Category | Advanced | Proficient | Developing | Beginning |
| --- | --- | --- | --- | --- |
| Research Understanding | Explains project, evidence, revisions, and limitations with depth. | Explains project clearly and accurately. | Explains some parts but lacks detail or clarity. | Struggles to explain the project accurately. |
| Evidence Explanation | Uses specific data and visuals effectively to support claims. | Uses evidence appropriately. | Mentions evidence but does not explain it fully. | Provides little or no evidence. |
| Visual Communication | Visual product is clear, readable, professional, and evidence-centered. | Visual product supports explanation. | Visual product is present but crowded or unclear. | Visual product is missing, confusing, or distracting. |
| Limitations and Future Work | Explains limitations and next steps thoughtfully. | Addresses limitations and future work. | Mentions limitations or next steps briefly. | Does not address limitations or future work. |
| Q&A | Answers thoughtfully with evidence, humility, and professionalism. | Answers questions accurately. | Answers some questions but lacks detail. | Struggles to answer basic questions. |
| Professionalism | Engages guests confidently and respectfully throughout. | Meets professionalism expectations. | Needs occasional reminders. | Does not meet event expectations. |

# 11. Post-Showcase Reflection and Follow-Up

Reflection should occur while the experience is fresh. The showcase is not only a final event; it is evidence of student growth in scientific communication.

## Student Reflection Prompts

What part of your presentation went best?

What question from the audience made you think the most?

How did your explanation improve through practice?

What evidence did you explain most clearly?

What limitation or uncertainty did you discuss honestly?

What would you change if you presented this project again?

What did you learn from hearing other students explain their research?

How has your understanding of scientific research changed since the beginning of the course?

## Teacher Reflection Prompts

Which parts of the event worked well logistically?

Which students were especially ready to communicate their work, and why?

Which students needed more preparation for Q&A?

Were visitors clear on their role?

Was the room layout effective?

Were the rubrics or feedback forms useful?

What should be changed before next year?

What evidence from the event should be saved for program advocacy?

## Thank-You Message Template

Subject: Thank You for Supporting the STARLAB Research Showcase

Dear [Name],

Thank you for attending the STARLAB Student Research Showcase. Your presence gave students an authentic audience for their research and helped them practice the kind of scientific communication that matters beyond the classroom. The questions, feedback, and encouragement students received will help them reflect on their work and continue growing as researchers.

We appreciate your support of student research and hope to continue building opportunities for students to engage in authentic science and engineering.

Sincerely,

[Teacher Name]

# 12. Showcase Archive Checklist

| Artifact | Save Location / Notes |
| --- | --- |
| Final student posters, slides, or board photos |  |
| Final research reports |  |
| Audience feedback forms |  |
| Presentation rubrics |  |
| Student reflections |  |
| Photos or videos, if permitted |  |
| Mentor or visitor list |  |
| Teacher reflection notes |  |
| Strong examples for next year |  |
| Program advocacy artifacts for administrators or district leaders |  |

# 13. Signage and Station Materials

## Suggested Event Signs

Welcome to the STARLAB Student Research Showcase

Visitor Check-In

Please Ask Students Questions

Poster Session Round 1 / Round 2

Do Not Touch Prototype Without Permission

Student Presentation Stations

Feedback Form Return Location

Thank You for Supporting Student Research

## Student Station Card Template

| Field | Content |
| --- | --- |
| Student Name |  |
| Project Title |  |
| Research Question or Engineering Goal |  |
| Project Type | Experimental / Engineering / Data Analysis / Computational / Observational / Other |
| One-Sentence Research Story |  |
| Ask Me About | My strongest evidence / My biggest limitation / What I would do next |

# Final Teacher Note

A strong STARLAB showcase does not require every project to have perfect results. It requires students to explain their work honestly, point to evidence, acknowledge limitations, and describe what they learned from the research process. The showcase should celebrate the product and the process.