# Week 12: Midpoint Review and Progress Reporting

## Teacher Overview

Week 12 marks a formal mid-project review. Students should pause to summarize what has been completed, what the data suggest so far, what challenges remain, and what needs to happen before analysis.

The mid-project progress report is both an accountability tool and a thinking tool.

## Weekly Objectives

Students will be able to:

- Summarize progress clearly.

- Describe preliminary data without overstating conclusions.

- Identify challenges and revisions.

- Explain next steps.

- Produce a mid-project progress report.

## Teacher Materials

Deck Use: No New Deck - midpoint review and progress reporting

- Student Handout 14: Mid-Project Progress Report

- Appendix N: Progress Report Rubric

- Appendix O: Midpoint Conference Questions

## Suggested Weekly Flow

### Day 1: What Belongs in a Progress Report?

Explain that a progress report should include:

- Project purpose

- Current research question or engineering goal

- Work completed so far

- Pilot testing results

- Method revisions

- Data collected so far

- Preliminary patterns or observations

- Challenges and limitations

- Next steps and updated timeline

### Days 2–3: Progress Report Drafting

Students draft the progress report using Student Handout 14.

Students should include at least one data table, graph draft, image, prototype photo, or organized evidence sample if available.

### Day 4: Peer or Teacher Review

Students exchange progress reports or meet with the teacher for brief feedback.

Review focus:

- Is the project status clear?

- Is the data described honestly?

- Are problems documented?

- Are next steps realistic?

### Day 5: Submit Progress Report

Students submit the mid-project progress report.

Teacher may use this report to identify students who need intervention before Unit 4.

## Week 12 Deliverables

- Mid-project progress report draft

- Peer or teacher feedback

- Final mid-project progress report

## Teacher Notes

This is a critical checkpoint. Students without usable data by Week 12 need a focused recovery plan. That may include reducing scope, simplifying a method, switching to analysis of existing data, or completing a smaller but defensible version of the original project.